Software Project Plan

Online Hospital Appointment & Patient Management System

Scope, Timeline, and Team Roles for a Sample Application

# 1. Introduction

This document presents the software project plan for the Online Hospital Appointment & Patient Management System, a sample healthcare application used earlier as the subject of a case study on the analysis of Software Development Life Cycle (SDLC) models. That case study concluded that an Agile approach, supported by DevOps practices, is the most suitable SDLC model for this application because of its need for continuous feature updates, changing healthcare compliance requirements, and rapid, safety-critical bug fixes.

Building on that conclusion, this project plan translates the recommended Agile/DevOps model into a concrete plan covering the project scope, delivery timeline, and team roles required to design, build, and deploy the system.

# 2. Project Scope

## 2.1 In Scope

The project delivers the four core modules identified in the case study:

- Patient Module — registration/login, doctor and hospital search, appointment booking, online payments, medical record access, and video consultations.

- Doctor Module — availability/schedule management, appointment accept/reject, prescription updates, and video consultations.

- Pharmacy Module — medicine inventory management, prescription order processing, and delivery tracking.

- Admin Module — user management, hospital/doctor verification, reporting, and analytics.

- Supporting infrastructure: payment gateway integration, video consultation infrastructure, and cloud deployment on AWS/Azure/Google Cloud.

## 2.2 Out of Scope

- In-hospital hardware integration (e.g., biomedical devices, IoT monitoring equipment).

- Insurance claim processing and third-party insurer integrations (future phase).

- Multi-language localization beyond English (future phase).

## 2.3 Project Objectives

- Deliver a secure, scalable platform for patient–doctor interaction and hospital administration.

- Enable rapid, iterative delivery of features using Agile sprints.

- Establish a CI/CD pipeline (DevOps) for fast, reliable, and safe releases.

- Ensure compliance with healthcare data-protection requirements throughout development.

# 3. Project Timeline

The project follows an Agile delivery model organized into six SDLC phases (as defined in the case study), executed through iterative sprints rather than a single linear pass. An indicative 24-week (6-month) schedule for the first release is outlined below; subsequent releases continue as ongoing 2-week sprints under Maintenance.

| Phase | Key Activities | Duration | Deliverables |
| --- | --- | --- | --- |
| 1. Requirement Analysis | Gather patient, doctor, and hospital requirements; define payment gateway and video consultation needs | Weeks 1–2 | Software Requirement Specification (SRS) |
| 2. System Design | Database, UI, architecture, and API design | Weeks 3–4 | UML diagrams, database schema |
| 3. Development (Sprints 1–4) | Build Login, Appointment, Payment, and Prescription modules | Weeks 5–14 | Working increments each 2-week sprint |
| 4. Testing | Unit, integration, system, and user acceptance testing (UAT) | Weeks 15–18 | Test reports, signed-off UAT |
| 5. Deployment | Cloud deployment, web server release, mobile app release | Weeks 19–20 | Production release (v1.0) |
| 6. Maintenance | Bug fixes, security updates, feature enhancements, performance tuning | Weeks 21–24 and ongoing | Patch releases, monitoring reports |

Because the recommended model is Agile with DevOps, Development, Testing, and Deployment activities overlap and repeat within each 2-week sprint rather than occurring strictly in sequence; the durations above indicate the overall first-release timeline.

# 4. Team Roles & Responsibilities

| Role | Responsibilities | Count |
| --- | --- | --- |
| Project Manager / Scrum Master | Sprint planning, backlog prioritization, stakeholder communication, risk tracking | 1 |
| Business Analyst | Requirement gathering from patients, doctors, and hospital admin stakeholders; SRS documentation | 1 |
| UI/UX Designer | Wireframes, UI design, usability testing for patient and doctor interfaces | 1 |
| Solution Architect | Overall system architecture, API design, database schema, cloud infrastructure design | 1 |
| Frontend Developers (React) | Patient, doctor, pharmacy, and admin web/mobile interfaces | 2 |
| Backend Developers (Java/Python, Node.js) | Login, Appointment, Payment, and Prescription module development; API implementation | 3 |
| Database Administrator | MySQL/PostgreSQL schema management, performance tuning, backups | 1 |
| QA / Test Engineers | Unit, integration, system, and UAT test design and execution | 2 |
| DevOps Engineer | CI/CD pipeline, cloud deployment (AWS/Azure/GCP), monitoring, release automation | 1 |
| Security & Compliance Specialist | Data protection, healthcare compliance review, security testing | 1 |

# 5. Assumptions & Constraints

## 5.1 Assumptions

- Third-party payment gateway and video consultation APIs are available and stable.

- Hospitals and doctors participating in the pilot will provide timely feedback each sprint.

- Cloud infrastructure (AWS/Azure/Google Cloud) is provisioned before development begins.

## 5.2 Constraints

- Healthcare data-protection regulations must be met before production deployment.

- Delivery timeline is fixed at 24 weeks for the first release; scope is adjusted via sprint backlog, not by extending the release date.

- Team size is fixed at the outset (see Section 4); scaling requires a change request.

# 6. Risk Management

| Risk | Impact | Mitigation |
| --- | --- | --- |
| Changing healthcare compliance requirements mid-project | High | Agile sprints allow requirements to be re-prioritized in the backlog each cycle |
| Payment gateway or video API downtime | Medium | Use vendor SLAs and implement fallback/retry mechanisms |
| Delayed stakeholder feedback (doctors/hospitals) | Medium | Schedule dedicated feedback sessions at the end of each sprint |
| Security vulnerabilities in patient data handling | High | Continuous security testing integrated into the CI/CD pipeline |

# 7. Conclusion

This project plan operationalizes the SDLC recommendation from the earlier case study: an Agile approach supported by DevOps practices. The 24-week phased timeline, cross-functional team structure, and sprint-based delivery model are designed to accommodate the frequent requirement changes, compliance needs, and rapid release cycles characteristic of a healthcare appointment and patient management platform, while the risk management and assumptions sections address the key uncertainties likely to affect delivery.